## Read
Project Title: | Power Line Tethered Drone System
Student Name ( First, Last ) | email | Faculty (First, Last) | email
Brian Vu | brianqvu@mail.usf.edu | Dr. Wilfrido Moreno | wmoreno@usf.edu
Adam Woughter | woughtera@mail.usf.edu | Robert Tufts | tufts@usf.edu
Joey Ellis | jellis8@mail.usf.edu
Talha Bin Amir | talhabinamir@mail.usf.edu

## Accomplishments
Tri-Weekly status. The content of the weekly communication is: a) Program schedule, technical and cost status b) Significant accomplishments c) Issues and resolution plans d) Action items status e) Provide date and time of meeting with the advisor The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2018-09-10 | Research done | Flight Controller options found. Thermal camera options found
2 | 2018-09-10 | Weekly meeting with Dr. Moreno | Went over things that need to be done such as ConOps document
3 | 2018-09-10 | Weekly team meeting | Discussed objectives. Worked on the triweekly report
4 | 2018-09-17 | Weekly Meeting with Dr. Moreno | Discussed ConOps document. Set a conference call meeting with FPL Subject matter Expert (SME) for 9/26/18 at 8am
5 | 2018-09-26 | First Meeting with Dr. Moreno and Eric Schwartz (FPL Subject Matter Expert (sme)) | Went over FPL drone proposal #1 and proposal #3 expectations/goals. Discussed general requirements (i.e. must fly about 100-200 feet), USF has rules and regulations on flying a drone a certain height). We must also be marketing our drone as personal and not a commercial project. For proposal #1, FPL would like to add a camera system, however it is not part of the basic expectation from our team. For proposal #3, the team must build a drone that is capable of 24+ hour flight, waterproof, may be able to withstand strong winds (25+ mph), livestream video capability.
6 | 2018-10-03 | 2nd Meeting with Dr. Moreno & Eric Schwartz | Went over the system expectations and estimated cost for proposal #1 and proposal #3. For proposal #1, press a button, take off, fly a path, and return back. For proposal #3, capable of 24+ hour flight, waterproof, livestream video capability. Also discussed scenarios on what the drone would be doing for each proposal. For proposal #1, FPL would like to take pictures of the transformer of what would not have been able to see from the ground. For proposal #3, the drone could be used during a hurricane (video surveillance), security site, office site (video monitoring).
7 | 2018-10-10 | 1st Meeting with Robert Tufts (Drone Connoisseur/expert) | System level breakdown: hardware trade off studies. We discussed: motors, electronic motor control, camera system, camera stabilizer (gimbal), landing gear, landing pads, processor (pixhawk), software program (ardupilot). Briefly talked about how all system connects and interfaces together: See conops document for picture of system layout integration (motor-ESC-flight controller). Robert Tufts lended the team one of his drones to practice piloting with.
8 | 2018-10-17 | 3rd Meeting with Dr. Moreno & Eric Schwartz (FPL Subject Matter Expert (sme)) | Briefly talked about the expectations of drone, went over Conops Version 3 with followup questions.
9 | 2018-10-21 | Team meeting to start the process of build a prototype drone | The team will use this time to begin the process of assembling a prototype drone, and will also talk about team assignments, team roles, team due dates, decide parts/processors, order processor. Team started building the quadcopter frame.
10 | 2018-10-31 | 4th Meeting with Dr. Moreno and Eric Schwartz | Discussed narrowing of group design with Eric Schwartz. Eric expressed a desire to prioritize longer flight time over large load bearing. Discussed possible methodology of detecting transmission lines. Assesed challenge of landing on a moving target, will need to revisit the extent stakeholder need. Decided a formal presentation and discussion of proposed designs was necessary moving forward.
11 | 2018-11-04 | 2nd team meeting for practice quadcopter build | Completed the quadcooter frame. Soldered ESCs to motors. Soldered wires to gyroscope pins
12 | 2018-11-07 | 2nd meeting with Robert Tufts | Presented potential designs. Discussed designs with Robert and found problems and solutions. Robert brought his own builds and other components to show the team. Discussed budgetting for spare parts and tools. Discussed further requirements that need to be met for the build, such as picture quality. Robert recommended more parts that could be implemented on the build.
13 | 2018-11-21 | 5th team meeting with Dr. Moreno and Eric Schwartz | Propsed design approved by advisor and SME. Ordering parts process begun.

## Action Register
# | Date Created | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
1 | 2018-09-10 | Joseph Ellis | Researched Drone dimensions,and framing materials | Joseph Ellis | 2018-09-14 | Closed | -
| 2018-09-10 | Joseph Ellis | Came up with a list of questions for the upcoming meeting with FPL to understand | Joseph Ellis | 2018-09-14 | Closed | -
| 2018-09-10 | Joseph Ellis | Researched Workswell GIS Thermal Camera | Joseph Ellis | 2018-09-14 | Closed | -
2 | 2018-09-10 | Talha | Research for flight controllers | Talha | 2018-09-14 | Closed | - | • Pixhawk flight controller found • QGroundcontrol and Mission Planner softwares found
| 2018-09-10 | Talha | Research on drone frames and bases | Talha | 2018-09-14 | Closed | -
| 2018-09-10 | Talha | Came up with some questions to ask at the FPL meeting to get a better idea of the project | Talha | 2018-09-14 | Closed | -
| 2018-09-10 | Talha | Scheduled a weekly meeting with the team | Talha | 2018-09-14 | Closed | -
3 | 2018-09-10 | Adam | Research for autonomous microcontroller code | Adam | 2018-09-14 | Closed | -
| 2018-09-10 | Adam | Wrote out questions to ask FPL at the meeting | Adam | 2018-09-14 | Closed | -
4 | 2018-09-10 | Brian | Created Drone Procedure, hours log, resources doc | Brian | 2018-09-14 | Closed | -
| 2018-09-10 | Brian | Research on hardware building, program/software (self-leveling) | Brian | 2018-09-14 | Closed | -
| 2018-09-10 | Brian | Set up advisor - Dr. Moreno and talk about opportunities and resources | Brian | 2018-09-14 | Closed | -
| 2018-09-10 | Brian | Determined questions for FPL proposals/limitations/objectives/hardware,software process, details | Brian | 2018-09-14 | Closed | -
| 2018-09-10 | Brian | Researched and bought some drone parts | Brian | 2018-09-14 | Closed | -
| 2018-09-10 | Brian | Set up Team communication - group text, drive folder | Brian | 2018-09-14 | Closed | -
5 | 2018-09-16 | Talha | Finalized the Triweekly Report #1 | Talha | 2018-09-17 | Closed
| 2018-09-17 | Talha | Created and formatted a ConOps document | Talha | 2018-09-17 | Closed | -
| 2018-09-19 | Talha | Created, formatted and worked on rev0 of ConOps document | Talha | 2018-09-24 | Closed | -
| 2018-09-26 | Talha | Worked on rev1 of ConOps document | Talha | 2018-10-02 | Closed | -
| 2018-09-28 | Talha | Did research on powerline tethered drone systems | Talha | 2018-09-28 | Closed | -
| 2018-09-28 | Talha | Did research on customizing off the shelf drones for autonomy | Talha | 2018-09-28 | Closed | - | dji API SDK can be used for modifying DJI firmware
6 | 2018-10-07 | Joseph | Updated the ConOps document to be adaptable for both proposals | Joey | 2018-10-07 | Closed
7 | 2018-09-26 | Team | 1st Meeting with Dr. Moreno and Eric Schwartz (FPL) | Team | 2018-09-26 | Closed |  | • Went over FPL drone proposal #1 and proposal #3 expectations/goals. Discussed general requirements (i.e. must fly about 100-200 feet), USF has rules and regulations on flying a drone a certain height). We must also be marketing our drone as personal and not a commercial project. For proposal #1, FPL would like to add a camera system, however it is not part of the basic expectation from our team. For proposal #3, the team must build a drone that is capable of 24+ hour flight, waterproof, may be able to withstand strong winds (25+ mph), livestream video capability.
8 | 2018-10-03 | Team | 2nd Meeting with Dr. Moreno and Eric Schwartz (FPL) | Team | 2018-10-03 | Closed |  | Went over the system expectations and estimated cost for proposal #1 and proposal #3. For proposal #1, press a button, take off, fly a path, and return back. For proposal #3, capable of 24+ hour flight, waterproof, livestream video capability. Also discussed scenarios on what the drone would be doing for each proposal. For proposal #1, FPL would like to take pictures of the transformer of what would not have been able to see from the ground. For proposal #3, the drone could be used during a hurricane (video surveillance), security site, office site (video monitoring).
| 2018-10-10 | Team | Meeting with Robert Tufts (Director of the USF Center of Nanotechnology) who is an expert on drones | Team | 2018-10-10 | Closed |  | Got a lot of useful information from Robert about batteries, frames, motors, props, etc. Realized we will probably need a hexacopter or maybe even an octocopter depending on our payload size. Discussed the Pixhawk flight controller that we were looking into and Robert approved the choice. Robert also suggested to start learning how to pilot drones. Robert also donated a small drone to the team for pilotting practice.
9 | 2018-10-14 | Talha | Updated ConOps document | Talha | 2018-10-16 | Closed |  | Added more detailed descriptions of the required project and also detailed descriptions of the teams first proposed design.
10 | 2018-10-14 | Team | Updated ConOps document | Team | 2018-10-16 | Closed |  | Added questions to FPL, updated systems requirement (section 4), added scenarios (section 3).
11 | 2018-10-14 | Talha | Did research on drone batteries | Talha | 2018-10-21 | Closed
| 2018-10-14 | Talha | Did research on wireless charging |  |  |  |  | Looked for possibility of adding wireless charging to the drone. Will propbably need to create our own wireless charging system, but should not require a lot of work.
12 | 2018-10-17 | Team | 3rd Meeting with Dr. Moreno and Eric Schwartz (FPL) | Team | 2018-10-17 | Closed |  | Discussed and presented our first proposed basic design. Went over some more details about the requirements. Discussed adding a Validation, Maintenance and Decommisioning section to the ConOps document. Discussed adding two more design ideas to the ConOps: A hybrid of proposal #1 and #2 built by ourselves and another design that could use an off the shelf drone.
13 | 2018-10-12 | Joseph | Practice piloting a practice drone | Joseph | 2018-10-22 | Closed
14 | 2018-10-22 | Talha | Practice piloting a practice drone | Talha |  | Closed
| 2018-10-19 | Talha | Updated ConOps document | Talha | 2018-10-23 | Closed |  | Added two more possible designs to the ConOps. Created Maintenance, Validation and Decommissioning sections to the ConOps. Added more detail to the main design. Added the practice design the team is working on. Added Components sections for each design.
15 | 2018-10-21 | Team | Team Meeting to begin process of building prototype | Team | 2018-10-21 | Closed |  | • Start the process of building prototype. • Determine team assignments, due dates, team roles, select board that we are going to use, hardware tradeoffs,
16 | 2018-10-22 | Talha | Did research on wireless charging | Talha | 2018-10-27 | Closed
| 2018-10-27 | Talha | Built a wireless circuit to power an LED wirelessly | Talha | 2018-10-29 | Closed |  | Not really a complicated task and wireless charging should be easy to implement.
| 2018-10-29 | Talha | Working on building a wireless charging system to charge a small practice drone | Talha | - | Open |  | Completed a circuit design for charging a one cell battey. Not yet built. Also designed a system for charging a multicell battery but have not yet built or tested either.
| 2018-10-29 | Talha | Updated ConOps document | Talha | 2018-11-04 | Closed |  | rev5. Added more detail about wireless charging and a secondary charging system.
| 2018-10-29 | Adam | Did research on motors | Adam | 2018-11-20 | Closed
| 2018-10-29 | Adam | Did research on batteries | Adam | 2018-11-20 | Closed
| 2018-10-29 | Adam | Updated ConOps document | Adam | 2018-10-31 | Closed |  | Updated the compnents list for Design 1 with a potential motor and battery
| 2018-11-04 | Team | 2nd Meeting for practice build | Team | 2018-11-04 | Closed |  | Completed quadcopter frame. Soldered ESCs to motors.
| 2018-11-05 | Talha | Updated ConOps document | Talha | 2018-11-12 | Closed |  | Added components and prices for different designs
| 2018-11-05 | Talha | Worked on Design Comparison Presentation | Talha | 2018-11-12 | Closed |  | Dr. Moreno asked for a Design Comparison (Pros and Cons) presentation to be presented to him and Robert tufts. Created, designed and worked on the presentation.
| 2018-11-05 | Talha | Research on different programming softwares | Talha | 2018-11-12 | Closed |  | Researched the Ardupilot and DJI SDK softwares and uses. Researched Ardupilot Mission Planner too. These softwares can be used after a supported flight controller for either is purchased.
| 2018-11-18 | Talha | Updated ConOps document | Talha | 2018-11-21 | Closed |  | Added recomende designs and fixed formatting
| 2018-11-22 | Talha | Updated ConOps document | Talha | 2018-11-25 | Closed |  | Added more parts necessary for the project to BOM

## Org Chart
Team Member | Role | Role Description
Dr. Moreno | Team Advisor | 1) Peronsally advise the team. 2) Provide resources to the team (personnel, equipment, point of contacts). 3) Direct the team in the direction of completing set expectations and goals 4) Provide electrical engineering advisement/knowledge
Brian Vu | Engineer | 1) Responsible for taking notes. 2) Researching: parts, system requirement, programming requirement.
Adam Woughter | Engineer | 1) Responsible for taking notes. 2) Researching: parts, system requirement, programming requirement.
Joey Ellis | Engineer | 1) Responsible for taking notes. 2) Researching: parts, system requirement, programming requirement.
Talha Bin Amir | Engineer | 1) Responsible for taking notes. 2) Researching: parts, system requirement, programming requirement.

## Project Schedule
[7 empty] | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22
| Design I | [16 empty] | Design II - subject to change per design II Intructor
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Needs to Align with Instructors deadlines
Intructors Milestones | bar: Design I 4; Design I 11; Design I 16
[11 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established
WBS, Org. and Schedule due, embeded in excel | bar: Design I 7
Requirements Doc Due ( Preliminary & Final ) | bar: Design I 10
Final Document Package due
Team/Student needs to provide further schedule detial to accomplish the tasks | [33 empty] | < Please modify this section of schedule per your project
Planning and Systems Engineering
Product Idea/Concept | bar: Design I 2 to Design I 4; Design I 7
SME Meeting
System Engineering Management Plan | bar: Design I 2 to Design I 3; Design I 8; Design I 10; Design I 16
|  | ConOps Formatted | [5 empty] | ConOps Submitted | [7 empty] | Finish developing system part list (submit to FPL to buy) 11/26/18
System Requirements Document (SRD) | bar: Design I 2 to Design I 3; Design I 16
Finish distinguishing all systems on the drone and how they come together, 11/26/18
Desing Document
Major Design Deadlines
Design, Procure, Build, & Test | bar: Design I 8; Design I 12; Design I 15; Design II - subject to change per design II Intructor 18
[8 empty] | Design |  |  |  | Procure |  |  | Completely build the Quadcopter drone hardware |  |  | Test the software, run, and complete software | Fly the quadcopter |  |  |  |  | Hexacopter Hardware Completely built
Sub Design and Development Tasks
Electrical PWB Design / Design Center | bar: Design I 16
Software/FPGA Design & Development | bar: Design I 16
Mechanical Design | bar: Design I 16
SW Design (ABI, Boot, BSP, TSW) (Initial Drops) | bar: Design I 16
Procure / Build Hardware
Test & Integrate H/W
Assumptions:
1. List critical schedule assumptions, dependcies

## WBS
Porject Title: | FPL Drone system
Student Name ( First, Last ) | email | Faculty (First, Last) | email
Brian Vu | brianqvu@mail.usf.edu | Dr. Wilfrido Moreno | wmoreno@usf.edu
Adam Woughter | woughtera@mail.usf.edu
Joey Ellis | jellis8@mail.usf.edu
Talha Bin Amir | talhabinamir@mail.usf.edu
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT |  | **All member should be involved in all tasks
Technical Leader | Talha | • Keeping track of objectives and making sure the team completes them as well as on time,
Team Coordination Leader | Adam, Brian | * scheduling meetings with Dr. Moreno, and FPL and Robert
Cost & Schedule leader | Joey | * Parts and design schedule
SYSTEM ENGINEERING |  | **All member should be involved in all tasks
SYST ENGINEERING | Brian | * Making sure all systems communicate and work together.
SYST ENGINEERING | Adam
TEST ENGINEERING | Talha | Making sure all processes are functioning as they should
PROD ENGINEERING | Team
CONFIG MGMT | Brian | * Putting the parts together. Assembly.
RELIABILITY | Team
QUALITY | Team
PARTS MANAGEMENT | Joey
EMI / EMC | Brian | * Proper shielding on wires, microprocessor
SAFETY | Team
Hardware |  | **All member should be involved in all tasks
ELECT.DESIGN
DESIGN | Talha, Joey, Adam, Brian | * Correct pin schematic layout, wiring to sensors, wiring to arduino board
MECH. DESIGN |  | **Every member should be responsible/involved
PSNA DESIGN | Team
SOFTWARE |  | **Every member should be responsible/involved
SW DEVELOPM | ALL team members
TEST Engineering |  | **Every member should be involved for testing
Test | Talha, Brian, Joey, Adam
TEST SOFTWARE |  | **Every member should be responsible/involved
DESIGN LEAD | Adam and Joey
Talha |  | Leading and completing FPL objectives - thermal Camera, Mobile Platform, notification system, real time communication, camera (take pictures to send back to engineers), off-road tether system
Joey |  | PCB design , 3 modeling, accounting
Adam |  | Arduino, electrical wiring, soldering, programming
Brian |  | Systems level overheading on flight mechanics

## BOM
Index | Component Name | Short description | Function | Quantity | Cost (without shipping) | Reference or links to websites
1 | Frame | Tarot T960 | This will be the base for all the other components. All tthe other components such as the battery, flight controller, etc will be placed on the frame | 1 | 399 | http://www.helipal.com/tarot-t960-hexacopter-frame-set.html
2 | Flight controller | PixHawk 4 | This will be used to control and program the drone using the ArduPilot and MissionPlanner softwares. This flight controller also has a barometer, gyroscope and several other useful components | 1 | 256 | https://docs.px4.io/en/flight_controller/pixhawk4.html ; https://www.amazon.com/Pixhawk-FMUv5-Autopilot-NEO-M8N-Management/dp/B07DQDXQSH/ref=sr_1_3?ie=UTF8&qid=1542767969&sr=8-3&keywords=pixhawk+4
3 | Battery | TATTU 7000mAh 6s 25c Lipo (Lifetime of ~24 min.) | This will provide power to the whole system | 1 | 150 | https://www.getfpv.com/tattu-7000mah-6s-25c-lipo-battery.html
4 | Motors | Tarot TL96020 5008 340KV motor | These will be used to turn the propelors and enable the drone to fly | 6 | 312 | https://www.hobby-wing.com/tl96020-5008-motor.html?gclid=CjwKCAiAiuTfBRAaEiwA4itUqE_Iq-Td4yrEnsWmGMjDYil6GdelC6B21a_vPMoPT9S1RCa2c5DzvBoCWIQQAvD_BwE
5 | Propellers | Quanum Carbon Fiber T-Style Propeller 18x5.5 | These will enable the drone to fly by creating lift forces | 3 (3 sets of 2) | 33 | https://hobbyking.com/en_us/quanum-carbon-fiber-t-style-propeller-18x5-5-cw-ccw-2pcs.html
6 | Transmitter & Receiver | FRSky Taranis X9D Plus & X8R | These will allow contact between the drone and the pilot | 1 | 245 | https://www.getfpv.com/frsky-taranis-x9d-plus-2-4ghz-accst-radio-x8r-combo-mode-2.html
7 | Sensors | Parallax PING Ultrasonic Sensor | These will allow the drone to detect obstacles and also land safely | 5 | 150 | https://www.parallax.com/product/28015
8 | LEDs | 2 Green and 2 Red | This will allow the pilot to differentiate between the front and the back of the drone | 4 | TBD
9 | Camera | Runcam | This will give the pilot a first person view (FPV) of the drone flight | 1 | 80 | https://shop.runcam.com/runcam2
9 | Camera | FLIR Duo | This will allow thermal imaging for powerline inspections | 1 | $799 (sale price; original $999) | https://www.flir.com/products/duo/?creative=258415154360&keyword=&matchtype=&network=g&device=c&gclid=Cj0KCQiA_s7fBRDrARIsAGEvF8SQRc60vvEGBj4ySJ4l_h42-WPKoM2ISU_0CMT4bQRZjaGVy-2soswaApwcEALw_wcB
10 | Camera Stabilizer (Gimbal) | 2 Axis Runcam 2 Micro Stabilized Gimbal | This will allow the runcam camera to be produce steady images and videos | 1 | 70 | https://copterlab.com/2-axis-runcam-2-hd-micro-gimbal
11 | ESCs | Spedix ES30 HV 3-6s BLHeLi_S 30A ESC | The Electronic Speed Controllers control the speed of the motors individually to maneuver the drone | 6 | 95 | https://www.getfpv.com/spedix-es30-hv-3-6s-blheli-s-30a-esc.html
12 | Software | ArduPilot, MissionPlanner and PX4 | These will allow the creation of autonomous programs and flight plans for the drone | - | Free
| TOTAL |  |  | ~$2600