## Read
Project Title: | Autonomous Drone for Power Grid Inspections
Student Name ( First, Last ) | email | Faculty (First, Last) | email
Brian Vu | brianqvu@mail.usf.edu | Dr. Wilfrido Moreno | wmoreno@usf.edu
Adam Woughter | woughtera@mail.usf.edu | Robert Tufts | tufts@usf.edu
Joey Ellis | jellis8@mail.usf.edu
Talha Bin Amir | talhabinamir@mail.usf.edu

## Accomplishments
Bi-Weekly status. The content of the weekly communication is: a) Program schedule, technical and cost status b) Significant accomplishments c) Issues and resolution plans d) Action items status e) Provide date and time of meeting with the advisor The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2019-01-11 | Quadcopter built. Calibration setup physical and software complete. Motor/vibration calibration software setup Complete. Some flight software work done.
2 | 2019-01-18 | Brian: Download opentx, made 2 models on opentx software, updated conops to include decomissioning the drone, upload picture of the team to website Joey: Finished soldering motors and ESC's Adam: Worked collectively with team Talha: Worked on the hexacopters wiring, mounting motors and escs, etc.
3 | 2019-01-25 | Brian: Transfer the 2 models on opentx software to the transmitter, Assigned AETR (Aileron, Elevate, Thrust, Rudder) to Channels 1-4, take drone registration safety quiz with Joey. Joey: Finished soldering power distribution board, take drone registration safety quiz with Brian Adam: Soldered connectors for the receiver. Worked on integration of receiver with Pixhawk Talha: Configured and calibrated the Pixhawk 4 flight controller. Soldered the Power Distribution Board wiring. Ordered parts needed.
4 | 2019-02-01 | Complete interview with Dr. Castellanos. Suggested we go over numbers - talking about fatalities
5 | 2019-02-08 | Talked to Dr. Moreno and Eric Schwartz, we are not allowed to leave permanent embellishment on drone saying sponsored by FPL. Have something detachable. Register drone after this week. We will aim to be capable of flying Week 6. Thursday, we should connect our new (better) receiver (x8), and we will have the battery charger connector so that we can fully charge the battery. With a full charge, we will then run the motors and system. *********Parts (telemetry, new receiver, connector came in) We are charging battery now. Firmware updated on runcam and communication connection successful with phone.
6 | 2019-02-15 | Landing gear communication completed, control landing gear up and down, transmitter to landing gear receiver servo connected, pdb and pixhawk mounted, vtx soldered connected pdb, assembled all connections wires (soldered) to battery charger, powered drone, research vtx transmitter,
7 | 2019-02-22 | Starting Week 7, we have to be present in class for other classmates CDR presentations. ****************Our next step/goal for the team, is to get the drone motors to be spinning **************** Starting Sunday 2/24 we will be performing a motor test and gps test to be ready for a flight test | Meeting with Dr. Moreno, he wants us to look into the thermal camera. We responded that we would look at it and make a trade analysis.
8 | 2019-03-01 | Team assigned who speaks what for CDR. Team practiced for the CDR Presentation. Perform Motor test, GPS test. Presented CDR to the Design 2 Class. We did well in our presentation. We believe we got a perfect/near perfect score. Got motors 5/6 spinning and operating. Arming and disasming GPS module. We will be looking to complete flight test next weekend by Sunday 3/10/19.
9 | 2019-03-08 | Team performed 2 flight test, both failed. We concluded that the problem may be from the ESC and that there is a disproportionate distribution of power from all motors. The problem: The first fail, the drone flipped to the left. The second fail, the drone flipped backward. We conclude that not all motors are performing at maximum power. Therefore, the ESC's must be calibrated and set to the same power.
10 | 2019-03-15 | Team found drone case and foam we can buy from Home Depot.
11 | 2019-03-22
12 | 2019-03-29
13 | 2019-04-05
14 | 2019-04-12
15 | 2019-04-19

## Action Register
# | Week | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
2019-01-11 | Week 1 | Talha | Put together the Hexacopter frame. | Talha | 2019-01-11 | Closed | - | Frame put together and completely built. Landing gear not put on yet due to the upward orientation (will take too much space). Landing gear will be put on once the drone is powered on.
2019-01-11 | Week 1 | Brian | Made website, made pages-header, product inventory, contact. Wrote up safety regulations from the FAA and registration website into our conops section. Finished writing the description to the website product inventory, about, intro. Find product pictures, and gridline drone inspection pictures. Book nanotech conference room as our biweekly meeting/working space with Sclafani-front desk | Brian | 2019-01-11 | Closed
2019-01-11 | Week 1 | Adam | Worked collectively with the team | Adam | 2019-01-11 | Closed |  | We finished building the quadcopter. We finished the calibration setup physical and software. We finished the motor/vibration calibration software setup. We are in the last phase of uploading flight software and are ready to perform flight test on quadcopter
2019-01-11 | Week 1 | Joey | Begin constructing motors to the drone | Joey | 2019-01-11 | Closed
2019-01-18 | Week 2 | Talha | Worked on the hexacopters wiring, mounting motors and escs, etc. | Talha | 2019-01-18 | Closed | - | Wiring complete. ESCs connected to motors. Both ESCs and motors mounted. Wires tucked inside the arms. ESCs connected to PCB.
2019-01-18 | Week 2 | Brian | Download opentx, made 2 models on opentx software, updated conops to include decomissioning the drone, upload picture of the team to website | Brian | 2019-01-18 | Closed
2019-01-18 | Week 2 | Adam | Worked collectively with the team | Adam | 2019-01-18 | Closed
2019-01-18 | Week 2 | Joey | Finished soldering motors and ESC's | Joey | 2019-01-18 | Closed
2019-01-25 | Week 3 | Talha | Configured and calibrated the Pixhawk 4 flight controller. Soldered the Power Distribution Board wiring. Ordered parts needed. | Talha | 2019-01-25 | Closed | - | QGroundControl downloaded. Firmware uploaded on to the Pixhawk. Compass and Gyroscope calibration complete. PDB soldered and wired. New required parts for wiring and X8R reciever ordered.
2019-01-25 | Week 3 | Brian | Transfer the 2 models on opentx software to the transmitter, Assigned AETR (Aileron, Elevate, Thrust, Rudder) to Channels 1-4, take drone registration safety quiz with Joey. | Brian | 2019-01-25 | Closed
2019-01-25 | Week 3 | Adam | Soldered connectors for the receiver. Worked on integration of receiver with Pixhawk | Adam | 2019-01-25 | Closed
2019-01-25 | Week 3 | Joey | Finished soldering power distribution board, take drone registration safety quiz with Brian | Joey | 2019-01-25 | Closed
2019-02-01 | Week 4 | Talha | Connected the transmitter to the receiver, calibrate channels 1-4 on qground control. Ordered more parts that were needed. | Talha | 2019-02-01 | Closed | - | XSR reciever binded to transmitter and calibrated on QGroundControl. More required parts for battery wiring ordered.
2019-02-01 | Week 4 | Brian | Transfer Robert's model onto my opentx program, begin transfering over data from his model onto our transmitter, Connect transmitter to receiver, calibrate channels 1-4 on qground control, finish the systems design for the website and document, write a few questions and answer that might be addressed during the interview with Dr. Castellanos | Brian | 2019-02-01 | Closed
2019-02-01 | Week 4 | Adam | Work collectively with the team | Adam | 2019-02-01 | Closed
2019-02-01 | Week 4 | Joey | Finished soldering wires to battery charger | Joey | 2019-02-01 | Closed
2019-02-08 | Week 5 | Talha | Wired the Pixhawk 4. Put on landing gear on drone and connected the actuator. | Talha | 2019-02-08 | Closed | - | Pixhawk wiring complete. Landing gear assembled and working. PDB mounted and connected to PCB. ESC cables from PDB connected to PCB.
2019-02-08 | Week 5 | Brian | Created CDR powerpoint, doc, binded new receiver, write new special functions into model | Brian | 2019-02-08 | Closed
2019-02-08 | Week 5 | Adam | Filled out CDR section 1, worked on RunCam, updated firmware on Runcam and communication connection with phone sucecssful, worked on CDR, | Adam | 2019-02-08 | Closed
2019-02-08 | Week 5 | Joey | Calculated and verified the voltage/current settings to charge the LIPO battery | Joey | 2019-02-08 | Closed
2019-02-15 | Week 6 | Talha | FIxed landing geat to the drone frame and wired the actuator to the landing gear and PDB. Moved battery plate to the center of drone to improve center of gravity. Wired the pixhawk to the PDB. | Talha | 2019-02-15 | Closed
2019-02-15 | Week 6 | Brian | *Binded the new receiver to the drone to allow landing gear to deploy. I had to add special functions to channel 9 and 10 to allow the right switch to active down and up for ther landing gear. Next week, I should program to allow the landing gear to go up and down when the thrust level is at above or below 50% thrust. | Brian | 2019-02-15 | Closed
2019-02-15 | Week 6 | Adam | Researched VTX First person view goggles, soldered connectors for VTX transmitter to connect the RunCam to the VTX transmitter. Soldered the connectors to the Power distribution board on the drone | Adam | 2019-02-15 | Closed
2019-02-15 | Week 6 | Joey | Attached the landing gear, Drilled and attached the mount for the flight controller, Moved the battery compartment to the center of the drone so the device will stay balanced | Joey | 2019-02-15 | Closed
2019-02-22 | Week 7 | Talha | Wired the GPS to the pixhawk and tried running the motors. Configured failsafes using Qgroundcontrol. Worked on the test plan document. Worked on the CDR. |  | 2019-02-22
2019-02-22 | Week 7 | Brian | * Created the Test Plan Document, wrote the system pass/ fail criteria for communication system test, motor system test, flight test, autonomy test, gps test, battery system, and camera test. Added description to the pass pail criteria. Wrote critierias for all systems. Added the verification requirement from our conops document to the analysis part of the test plan document. Wrote demonstration and inspection section in the Test Plan document. Continued writing and editing the CDR presentation. Created and added high level system design flow diagram, component level system diagram, and data flow diagram to the CDR presentation. Edited the front page added team picture with advisors and team members information. | Brian | 2019-02-22 | Closed
|  | Adam | Reviewed and edited testing plan. Discussed plan for CDR presentation. Researched thermal camera option | Adam | 2019-02-22 | Closed
|  | Joey |  | Joey | 2019-02-22
2019-03-01 | Week 8 | Talha | Worked on making the motors run and getting a GPS lock. Got the transmitter model fixed and landing gear manual control on a switch. Creadted an organized version of the CDR and filled it up. Created PCB schematic. Identified the issue with the GPS lock and motors not working. Completed compass calibration. | Talha | 2019-03-01 | Closed |  | Failsafes were set to RTL and required a valid home set to arm the drone. Set failsafes to just a warning for now while drone is being calibrated.
2019-03-01 | Week 8 | Brian | Wrote the problem statement and solution in CDR, updated the high level system design and component level design and data flow diagram and software design. Formatted CDR. | Brian | 2019-03-01 | Closed
|  | Adam | Designed 3D printed mount for power distribution board. Calculated the battery life and thrust to weight ratio for CDR presentation. Participated in general drone build. | Adam | 2019-03-01 | Closed
|  | Joey | Charged Battery. Created and added Circuit Design of drone, motor system, flight system, and power distribution to the CDR presentation. | Joey | 2019-03-01 | Closed
2019-03-08 | Week 9 | Talha |  | Talha
|  | Brian | Researched more into the flir lepton thermal camera, we are capable of implementing it (it has been done) however time constraints, added all files into the website, | Brian | 2019-03-08 | Closed
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-03-15 | Week 10 | Talha |  | Talha | 2019-03-15
|  | Brian | Added Kill switch to channel 7 on the transmitter (radio). Added Return to home to channel 6 on the transmitter (radio). | Brian | 2019-03-15 | Closed
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-03-22 | Week 11 | Talha |  | Talha | 2019-03-22
|  | Brian |  | Brian
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-03-29 | Week 12 | Talha |  | Talha | 2019-03-29
|  | Brian |  | Brian
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-04-05 | Week 13 | Talha |  | Talha | 2019-04-05
|  | Brian |  | Brian
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-04-12 | Week 14 | Talha |  | Talha | 2019-04-12
|  | Brian |  | Brian
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-04-19 | Week 15 | Talha |  | Talha | 2019-04-19
|  | Brian |  | Brian
|  | Adam |  | Adam
|  | Joey |  | Joey
2019-04-26 | Week 16 | Talha |  | Talha | 2019-04-26
|  | Brian |  | Brian
|  | Adam |  | Adam
|  | Joey |  | Joey

## Org Chart
Team Member | Role | Role Description
Dr. Moreno | Advisor | 1) Peronsally advise the team. 2) Provide resources to the team (personnel, equipment, point of contacts). 3) Direct the team in the direction of completing set expectations and goals 4) Provide electrical engineering advisement/knowledge
Robert Tufts | Technical Advisor/Mentor | 1) Peronsally advise the team. 2) Provide resources to the team (personnel, equipment, point of contacts). 3) Direct the team in the direction of completing set expectations and goals 4) Provide electrical engineering advisement/knowledge
Talha Bin Amir | Engineer | 1) Building frame for hexacopter 2) Ordering parts and keeping track of orders. 3)Researching parts, system requirements, programming requirements. 4) Calibrating flight controller and setting up Qground control fir autonomous functions. 5) Making sure everyhting is on schedule.
Joey Ellis | Engineer | 1) Soldering wires, connectors and PDB. 2) Setting up battery charger an charging battery. 3) Researching parts, system requirements, programming requirement.
Adam Woughter | Engineer | 1) Reseaarching motors and battery values. 2) Researching and setting up FPV camera and FPV goggles. 3) Taking notes.
Brian Vu | Engineer | 1) Responsible for updating website and documents. 2) Setting up Transmitter - models on OpenTx Companion, as well on the transmitter remote, setting up special functions (landing gear, stationary, hover, etc). Channel selection - assign each channel to a special function or flight modee 3) X8R as well as any additional receiver connections

## Project Schedule
[7 empty] | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22
| Design I | [16 empty] | Design II - subject to change per design II Intructor
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Needs to Align with Instructors deadlines
Intructors Milestones | bar: Design I 4; Design I 11; Design I 16
[11 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established
WBS, Org. and Schedule due, embeded in excel | bar: Design I 7
Requirements Doc Due ( Preliminary & Final ) | bar: Design I 10
Final Document Package due
Team/Student needs to provide further schedule detial to accomplish the tasks | [33 empty] | < Please modify this section of schedule per your project
Planning and Systems Engineering
Product Idea/Concept | bar: Design I 2 to Design I 4; Design I 7
SME Meeting
System Engineering Management Plan | bar: Design I 2 to Design I 3; Design I 8; Design I 10; Design I 16
|  | ConOps Formatted | [5 empty] | ConOps Submitted | [7 empty] | Finish developing system part list (submit to FPL to buy) 11/26/18
System Requirements Document (SRD) | bar: Design I 2 to Design I 3; Design I 16
Finish distinguishing all systems on the drone and how they come together, 11/26/18
Desing Document
Major Design Deadlines
Design, Procure, Build, & Test | bar: Design I 8; Design I 12; Design I 15; Design II - subject to change per design II Intructor 18; Design II - subject to change per design II Intructor 24
[8 empty] | Design |  |  |  | Procure |  |  | Completely build the Quadcopter drone hardware |  |  | Test the software, run, and complete software | Fly the quadcopter |  |  |  |  | Hexacopter frame completely built
Sub Design and Development Tasks
Electrical PWB Design / Design Center | bar: Design I 16; Design II - subject to change per design II Intructor 24
Software/FPGA Design & Development | Design I 16: Wiring design of quadcopter completed; Design II - subject to change per design II Intructor 24: All connectors for wires of various parts soldered together.; Design II - subject to change per design II Intructor 26: Finalise wiring of the drone
Mechanical Design | Design II - subject to change per design II Intructor 32: Mechanical design finalized
SW Design (ABI, Boot, BSP, TSW) (Initial Drops) | Design I 16: Physical design/ parts selection agreed upon; Design II - subject to change per design II Intructor 32: Autonomous flight and imaging software finalized
Procure / Build Hardware
Test & Integrate H/W | Design II - subject to change per design II Intructor 26: Have all required parts on drone
Landing gear tested
Assumptions:
1. List critical schedule assumptions, dependcies | Design I 11: This schedule is based on the assumption that parts will not take a long time to arrive and the group has access to software design resources from the beginning

## WBS
Porject Title: | Autonomous Drone for Power grid Inspections
Student Name ( First, Last ) | email | Faculty (First, Last) | email
Talha Bin Amir | talhabinamir@mail.usf.edu | Dr. Wilfrido Moreno | wmoreno@usf.edu
Joey Ellis | jellis8@mail.usf.edu | Robert Tufts | tufts@usf.edu
Adam Woughter | woughtera@mail.usf.edu
Brian Vu | brianqvu@mail.usf.edu
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT |  | **All member should be involved in all tasks | **All member should be involved in all tasks
Technical Leader | Talha | * Keeping track of objectives, setting goals and making sure the team completes them as well as on time. | * Keeping track of objectives, setting goals and making sure the team completes them as well as on time.
Team Coordination Leader | Adam, Brian | * scheduling meetings with Dr. Moreno, and FPL and Robert | * scheduling meetings with Dr. Moreno, and FPL and Robert
Cost & Schedule leader | Talha | * Ordering parts and keeping track of all orders | * Ordering parts and keeping track of all orders
SYSTEM ENGINEERING |  | **All member should be involved in all tasks | **All member should be involved in all tasks
SYST ENGINEERING | Talha | * Making sure all systems are working as they should. | * Making sure all systems are working as they should.
SYST ENGINEERING | Adam
TEST ENGINEERING | Talha | * Making sure all processes are functioning as they should | * Making sure all processes are functioning as they should
PROD ENGINEERING | Team
CONFIG MGMT | Talha and Joey | * Putting the parts together. Assembly. | * Putting the parts together. Assembly.
RELIABILITY | Team
QUALITY | Team
PARTS MANAGEMENT | Talha | * Keeping track of parts and taking care of them and keeping them organized. | * Keeping track of parts and taking care of them and keeping them organized.
EMI / EMC | Team
SAFETY | Team
Hardware |  | **All member should be involved in all tasks | **All member should be involved in all tasks
ELECT.DESIGN
DESIGN | Team | * Correct pin schematic layout, wiring to sensors, wiring to arduino board | * Correct pin schematic layout, wiring to sensors, wiring to arduino board
MECH. DESIGN |  | **Every member should be responsible/involved | **Every member should be responsible/involved
PSNA DESIGN | Team
SOFTWARE |  | **Every member should be responsible/involved | **Every member should be responsible/involved
SW DEVELOPM | Team
TEST Engineering |  | **Every member should be involved for testing | **Every member should be involved for testing
Test | Team
TEST SOFTWARE |  | **Every member should be responsible/involved | **Every member should be responsible/involved
DESIGN LEAD | Talha
Talha |  | Leading and completing FPL objectives - thermal Camera, Mobile Platform, notification system, real time communication, camera (take pictures to send back to engineers), off-road tether system
Joey |  | PCB design , 3 modeling, accounting
Adam |  | Arduino, electrical wiring, soldering, programming
Brian |  | Systems level overheading on flight mechanics

## BOM
Order Date | Order Received Date | Vendor | Order Status | Part Name | Unit Price | No. Required | Total item Cost | Shipping | Total Order Cost | Overall Total | Budget | Balance
2018-12-20 | 2018-12-24 | GetFPV | Received | Pixhawk 4 Autopilot and Neo-M8N GPS Combo | 219.99 | 1 | 219.99 | 0 | 623.89 | 2553.67 | 3500 | 946.33
|  |  |  | Lumenier 51A BLHeli_32 32bit 2-6S w/Telemetry | 24.99 | 7 | 174.93
|  |  |  | ISDT Q6 Pro BattGo 300W 14A Battery balance Charger | 59.99 | 1 | 59.99
|  |  |  | Tattu Plus 10000mAh 22.2V 25C 6S Lipo Smart Battery Pack | 158.99 | 1 | 158.99
|  |  |  | Heat Shrink Tube Assortmentt Box - 508pcs Black | 9.99 | 1 | 9.99
2018-12-29 | 2019-01-11 | HeliPal | Received | Tarot X6 Hexacopter Build Kit | 1276 | 1 | 1276 | 180.11 | 1720.4
|  |  |  | Damper Mount for Flight Controller | 3.5 | 1 | 3.5
|  |  |  | RunCam 2 ActionCam (1080p/60fps) | 79.99 | 1 | 79.99
|  |  |  | PGY-Tech Fast Folding Landing Pad (Large/110cm) | 17.9 | 1 | 17.9
|  |  |  | Damping Mount for APM/Pixhawk FC | 3.9 | 1 | 3.9
|  |  |  | FXT Viper 5.8GHz FPV Goggles w/DVR | 159 | 1 | 159
2019-01-22 | 2019-02-01 | GetFPV | Received | ImmersionRC Tramp HV 5.8Hz Video Tx - (US Version) | 29.99 | 1 | 29.99 | 10.99 | 49.96
|  |  |  | XT60 Power Connectors (5 Pair) | 4.99 | 1 | 4.99
|  |  |  | EC5 to AS150 Power Adapter Cable | 3.99 | 1 | 3.99
2019-01-22 | 2019-01-28 | Amazon | Received | SanDisk Ultra 64GB microSDXC UHS-I card with Adapter | 12.49 | 1 | 12.49 | 0 | 51.44
|  |  |  | OliYin 3pcs Male XT-30 to Female XT-60 Connector Adapter | 10.98 | 1 | 10.98
|  |  |  | SIM&NAT RC Lipo Battery Charger Adapter Connector Splitter Cable | 9.99 | 1 | 9.99
|  |  |  | Tmaltide XT60 Plug Male Female Connector | 7.99 | 1 | 7.99
|  |  |  | Amass AS150 Male Female Anti Spark Connector Gold Plated Banana Plug Set | 9.99 | 1 | 9.99
2019-02-02 | 2019-02-07 | Amazon | Received | Youme 6 Pairs XT150 Connector Adapter Male Female Plug | 9.99 | 1 | 9.99 | 0 | 107.98
|  |  |  | FrSky Taranis Compatible Receiver X8R | 35.9 | 1 | 35.9
|  |  |  | NIDICI 12pcs M3 Anti-Vibration Fixed Screws Mounting Hardware Spacer | 7.88 | 1 | 7.88
|  |  |  | HolyBro 100mW Transceiver Telemetry Radio Set V3 (915Mhz) | 54.21 | 1 | 54.21